## Assessment & Plan
Stakeholder Assessment | [7 empty] | Stakeholder Management Plan
Type of stakeholder | Stakeholder Group / Individual | Impacted By | Impacts On | L of E Current | L of E Req’d | Information Needs | Purpose of Information | Channel | Frequency | Start Date | Person Responsible
A Council staff | Council managers/Finance dept | Impact of revenue loss. Could support local strategic initiatives | Gateway for inclusion in LTP or annual budgeting | 1 | 4 | Evidence and stories to support removing fines | Gain support to progress recommendation | Workshops, meetings, emails
A Council staff | Library management team | Needs to align with strategic plan and priorities | Needs support and engagement of this group to succeed | 3 | 5 | Understand purpose of project Evidence and stories, examples and templates | To engage their support
A Council staff | All staff | Affected by interactions with customers. Admin of collection | Success of implementation (interactions with customers) | 3 | 5 | Understand purpose of project and what will change | Inform of changes and their role in welcoming customers back | Emails, staff meetings etc
B Council Elected members | Elected members of Councils/Districts who support | Could support their aspirations for community | Decision makers - Allies | 1 | 5 | Evidence and stories to support removing fines | Engage as advocates
B Council Elected members | Elected members of Councils/Districts who disagree | Risk to concerns especially fiscal | Decision makers -Detractors - could defeat | 1 | 3 | Evidence and stories to support removing fines | reduce fears, change minds
B Council Elected members | Elected members of Councils/Districts who have no opinion or are unsure | Could support their aspirations for community if convinced | Decision makers - currently passive could support or not | 1 | 3 | Evidence and stories to support removing fines | reduce fears, change minds
C Residents and ratepayers | Customers of public libraries | Removal of barriers to use | Some may oppose because of fear of consequences Could provide great stories of personal impact | 1 | 3 | Understand experience of other libraries and actual consequences | Reduce fears, inform of full range of library services
C Residents and ratepayers | Non-users and lapsed users of public libraries | Removal of barriers to use | Could provide great stories of personal impact | 1 | 3 | What do libraries offer them. Barriers to use could be removed. | Attract to become users
D Other organisations | PLNZ Fines Free Working Group | Want to support libraries to make change | Can provide advice and tool-kits can reinforce messages, can amplify progress and good news stories | 5 | 5 | What are individual library networks doing and what support do they need | Ensure you have advice and support. Inform the Aotearoa landscape to support the broader campaign
D Other organisations | LIANZA | This would support professional community and remove barriers to access | Ally - can reinforce messages, can amplify progress and good news stories | 4 | 5 | What are individual library networks doing and what support do they need | Ensure you have advice and support. Inform the Aotearoa landscape to support the broader campaign
D Other organisations | LGNZ/SOLGM | Support the delivery of Wellbeings | Ally - can influence Council managers | 2 | 5 | Awareness and understanding of the case Evidence and stories to support advocacy | Engage their support to advocate for your case
E Community organisations | Social initiatives eg CAB, DECA | Supports communities of need | Potential ally | 1 | 4 | Awareness and understanding of the case Evidence and stories to support advocacy | Engage their support to advocate for your case
E Community organisations | Local Māori marae and organisations | Māori disproportionally affected by fines | Potential ally | 1 | 4 | Awareness and understanding of the case Evidence and stories to support advocacy | Engage their support to advocate for your case
E Community organisations | Targeted groups eg Age Concern, Grey Power, etc | Fines may negatively impact their constituents | Potential ally | 1 | 5 | Awareness and understanding of the case Evidence and stories to support advocacy | Engage their support to advocate for your case
E Community organisations | Friends of Library and volunteer groups | Want to improve reach of and use of libraries | Ally - can advocate to Council | 4 | 5 | Awareness and understanding of the case Evidence and stories to support advocacy | To engage and strengthen their advocacy on this topic
F Media | Local media/national media | Want a good story | May influence elected members and ratepayers. Publicity map bring back lapsed members | 2 | 3 | Wider context, local impact stories | Spread the word about the value of libraries and why fines are a barrier | Via Council comms team?
G Other?
L of E = Level of Engagement: 1 – Unaware, 2 – Aware, 3 – Understands, 4 – Committed, 5 – Advocate

## Notes
1 | The purpose of this assement and plan template is to help you understand who has an interest in this campaign and how they will impact the decision. Then you can plan to mitigate concerns or engage extra support
2 | This is a template - some stakeholders will not apply to you, or there may be others to include
3 | The Level of engagement scores may be different for your case. The key purpose is to identify the most important people in this decision and understand how to influence them L of E = Level of Engagement: 1 – Unaware, 2 – Aware, 3 – Understands, 4 – Committed, 5 – Advocate
4 | The assessment is one of the first things you should do. The plan can be developed as you do your research, or may not be so important in your organsation.
USE WHAT IS USEFUL, IGNORE WHAT IS NOT :)